## Overview
Pharmaceutical AI Platform – 2-Week Sprint Plan (Krishna & Nivas)
Phase 0 "Align & prepare" + platform foundation, then start of Phase 1 "Trusted research foundation" (PRD §15)
Project details
Project | Pharmaceutical AI Platform – evidence-grounded R&D assistant (per PRD)
Sprint 1 start | 2026-10-26 | Input – all schedule dates (Daily Schedule, Gantt headers) flow from this cell
Sprint 1 end | 2026-10-30
Sprint 2 start | 2026-11-02
Sprint 2 end | 2026-11-06
Team | Krishna – backend / AI / data (ingestion, retrieval, LangGraph, DB) • Nivas – frontend / platform / DevOps (UI, auth, CI/CD, containers, audit UI)
Target stack | Open-source on-premises candidates (PRD §12.2): React/Vite, FastAPI, Keycloak, PostgreSQL/pgvector, Tika/Tesseract, Sentence Transformers, LangGraph, vLLM, Podman. Azure equivalents (§11) if selected [confirm with client].
Sprint | Dates | Sprint goal | Demo / exit check | Key PRD requirements | Tasks (#)
Sprint 1 | 26 Oct – 30 Oct 2026 | Phase 0 "Align & prepare" + platform foundation: repo/CI, Podman dev environment, React/Vite UI shell, FastAPI skeleton, SSO (Keycloak or Entra ID [confirm with client]), PostgreSQL/pgvector schema, audit log baseline, project/role-based authorization. | Login via SSO → UI shell → authorized API call → audit entry visible; negative authorization tests green in CI. | FR-01, FR-02, FR-03, FR-30, NFR-01, NFR-02, NFR-07 | 15
Sprint 2 | 2 Nov – 6 Nov 2026 | Start Phase 1 "Trusted research foundation": document ingestion (Tika/Tesseract or Document Intelligence), chunking + embeddings, hybrid retrieval, evidence Q&A with citations/provenance via LangGraph with human-review gate, scientist UI question → cited answer, tests. | Ingest approved document → ask question → cited answer with provenance → review gate → audit trail, demoed to scientists. | FR-04, FR-05, FR-06, FR-08, FR-10, FR-11, FR-12, FR-28, NFR-06, NFR-10, NFR-12, NFR-13 | 14
Developer | Sprint | Focus area | Capacity (h) | Planned (h) | Utilisation
Krishna | Sprint 1 | Backend, AI & data – FastAPI, schema, authorization, audit, ingestion, retrieval, LangGraph | 30 | 25.25 | 84.17%
Nivas | Sprint 1 | Frontend, platform & DevOps – CI/CD, Podman, UI shell, SSO, audit UI, Q&A UI, E2E tests | 30 | 25.25 | 84.17%
Krishna | Sprint 2 | Backend, AI & data – FastAPI, schema, authorization, audit, ingestion, retrieval, LangGraph | 30 | 25.25 | 84.17%
Nivas | Sprint 2 | Frontend, platform & DevOps – CI/CD, Podman, UI shell, SSO, audit UI, Q&A UI, E2E tests | 30 | 24.25 | 80.83%
Ceremony | When | Purpose / agenda | Who | Timebox | Hours / sprint
Sprint planning | Monday 10:00 | Agree sprint goal, pull and estimate backlog items, confirm owners and dependencies. | Krishna, Nivas (+ product owner) | 2 h | 2
Daily stand-up | Mon–Fri 09:30 | Yesterday / today / blockers; update Status in the backlog. | Krishna, Nivas | 15 min | 1.25
Sprint review / demo + retrospective | Friday 14:00–16:00 | Demo working increment to stakeholders/scientists; retro: keep / improve / try; refine next backlog. | Krishna, Nivas, stakeholders | 1 h demo + 1 h retro | 2
Type | ID | Assumption / risk / dependency | PRD link | Impact & mitigation | Needed by
Dependency | D-01 | Client approval of authorized sources (regulatory, licensed literature, internal documents) for ingestion | FR-04, R-04, §17.3 | Blocks real-document ingestion in Sprint 2; mitigate with approved public/sample documents and record authorization basis per item. | 2026-10-30
Dependency | D-02 | Language model selection and licence approval (open-weight via vLLM, or Azure OpenAI) | NFR-15, NFR-21, R-08 | Needed for S2-09; build behind a model adapter and use a licence-cleared local dev model until approval. | 2026-11-02
Dependency | D-03 | ELN / LIMS access – read-only APIs or exports and data-owner approval | FR-09, R-05, §17.3 | Not needed in Sprints 1–2; request now so Phase 3 integration is not delayed. | 2026-11-06
Dependency | D-04 | Identity provider choice: Keycloak vs Entra ID [confirm with client] | FR-02, NFR-01 | Needed for S1-09; implement generic OIDC with a Keycloak dev realm so switching is configuration only. | 2026-10-27
Assumption | A-01 | Each developer has ~6 focus hours/day for 5 days per sprint; plan loaded to ~80–85% to absorb unknowns. | — | If capacity drops, defer Should items (S1-12, S1-14, S2-11, S2-13) first. | 2026-10-26
Assumption | A-02 | A scientist/SME joins the Sprint 2 demo and reviews sample cited answers. | NFR-12, NFR-13 | Without SME review the human-review gate is demoed with test reviewers only. | 2026-11-06
Assumption | A-03 | Development runs on Linux + Podman in a non-production environment; no regulated data in dev. | NFR-04, NFR-22 | Use synthetic or approved public documents; production hardening is out of scope for these sprints. | 2026-10-26
Risk | R-01 | LLM produces unsupported or inaccurate statements | R-01, FR-11, NFR-13 | Citation validation step, uncited-claim flagging and mandatory human review gate (S2-09, S2-10). | 2026-11-06
Risk | R-02 | Confidential content leaks via retrieval or model context | R-02, FR-10, NFR-06 | Authorization filters applied in SQL before model access; leakage test suite (S2-12). | 2026-11-06
Risk | R-03 | OCR / extraction errors enter answers | R-03, FR-05, FR-07 | Record extraction uncertainty now; scientist verification queue (FR-07) planned for the next sprint. | 2026-11-06

## Sprint Backlog
Sprint Backlog – Pharmaceutical AI Platform (Sprints 1–2)
Est. hours are per person; tasks owned by "Both" count in full for each developer. Status options: Not started / In progress / Blocked / Done.
ID | Sprint | Epic | User story / task | Description | Linked PRD req | Owner | Priority | Story points | Est. hours | Start date | End date | Status | Acceptance criteria / Definition of done | Dependencies
S1-01 | Sprint 1 | Sprint ceremonies | Sprint 1 planning & PRD walkthrough | Walk through PRD sections 8, 9, 11-12 and 15; agree Sprint 1 goal, task breakdown, estimates and Definition of Done. | PRD §15 Phase 0 | Both | Must | 0 | 2 | 2026-10-26 | 2026-10-26 | Not started | Sprint goal agreed; all S1 tasks estimated and owned; DoD (code reviewed, tests in CI, docs updated) agreed. | None
S1-02 | Sprint 1 | Sprint ceremonies | Daily stand-ups (5 × 15 min) | 15-minute daily stand-up at 09:30: progress, plan, blockers; update Status column. | — | Both | Must | 0 | 1.25 | 2026-10-26 | 2026-10-30 | Not started | Stand-up held each day; blockers logged on the board within the day. | None
S1-03 | Sprint 1 | Phase 0 – Align & prepare | Phase 0 alignment: scope, sources, access & success criteria | Confirm users, product scope, data owners, approved sources, identity provider, model licence route and success measures; log decisions and open items for the client. | FR-04, NFR-15, NFR-21, PRD §15 Phase 0 | Both | Must | 2 | 2 | 2026-10-26 | 2026-10-27 | Not started | Decision log shared with client; open questions (IdP, model licence, source approval, ELN access) have owners and due dates. | Client stakeholder availability
S1-04 | Sprint 1 | DevOps & CI/CD | Repository, branching & CI pipeline | Mono-repo (ui/, api/, infra/), branch protection, PR template; CI runs lint, unit tests, build and secret scanning on every PR. | NFR-03, NFR-21 | Nivas | Must | 2 | 3 | 2026-10-26 | 2026-10-27 | Not started | PR to main blocked unless CI green; secret scan finds no secrets; dependency licence report generated. | None
S1-05 | Sprint 1 | Platform foundation | FastAPI backend skeleton | FastAPI service with layered structure (routers, services, repositories), settings, health/readiness endpoints, OpenAPI docs and structured logging with OpenTelemetry hooks (redacted). | FR-01, NFR-20, NFR-22 | Krishna | Must | 3 | 4 | 2026-10-26 | 2026-10-27 | Not started | /health and /ready return 200 in container; OpenAPI published; unit tests ≥ 80% on skeleton; no sensitive content in logs. | S1-04
S1-06 | Sprint 1 | DevOps & CI/CD | Podman dev environment | Podman compose for API, PostgreSQL + pgvector, Keycloak, Nginx reverse proxy and Tika; one-command start with seed data and .env template. | NFR-18, NFR-22 | Nivas | Must | 2 | 3 | 2026-10-27 | 2026-10-28 | Not started | `make up` starts all services on a clean Linux host in < 10 min; README documents setup; no credentials committed. | S1-04
S1-07 | Sprint 1 | Data & audit | PostgreSQL/pgvector schema v1 + migrations | Alembic migrations for projects, users/roles, memberships, sources, documents & versions, chunks (vector column + access metadata) and audit_events; SQLAlchemy models and scoped repositories. | FR-06, FR-08, NFR-10 | Krishna | Must | 3 | 4 | 2026-10-27 | 2026-10-28 | Not started | Migrations run up/down cleanly in CI; pgvector extension enabled; ERD committed; repository tests pass. | S1-05, S1-06
S1-08 | Sprint 1 | Scientist UI | React/Vite UI shell | React + Vite + TypeScript app with routing, layout, navigation and placeholder views for Research & strategy, Trial verification and Report review; API client generated from OpenAPI. | FR-01 | Nivas | Must | 3 | 4 | 2026-10-28 | 2026-10-29 | Not started | Three workspace views reachable from navigation; app builds in CI; accessible colour contrast; calls /health via API client. | S1-04, S1-05
S1-09 | Sprint 1 | Identity & access | SSO integration (OIDC) – Keycloak or Entra ID [confirm with client] | OIDC authorization-code + PKCE login in UI, token refresh/logout; Nginx/gateway rejects unauthenticated requests. Built IdP-agnostic; Keycloak realm in dev until client confirms provider. | FR-02, NFR-01 | Nivas | Must | 3 | 4 | 2026-10-28 | 2026-10-29 | Not started | Unauthenticated calls return 401; login → token → API call works end to end; IdP choice recorded [confirm with client]. | S1-03 (IdP decision), S1-06
S1-10 | Sprint 1 | Identity & access | Project & role-based authorization in API | JWT validation in FastAPI; project membership and role (scientist, reviewer, admin) checks plus object-level guards on every endpoint via dependency injection. | FR-03, NFR-02 | Krishna | Must | 3 | 4 | 2026-10-28 | 2026-10-29 | Not started | User with valid token cannot read/act on another project's objects (negative tests); roles enforced server-side, not only in UI. | S1-07, S1-09
S1-11 | Sprint 1 | Data & audit | Audit log baseline | Append-only audit_events (who, what, when, object, version, outcome) written by a service-layer decorator; kept separate from operational telemetry; UPDATE/DELETE revoked on table. | FR-30, NFR-07, NFR-08 | Krishna | Must | 3 | 4 | 2026-10-29 | 2026-10-30 | Not started | Login, access and project actions produce audit rows; audit rows cannot be updated or deleted by app role; reconstruction query returns who/what/when. | S1-07, S1-10
S1-12 | Sprint 1 | Data & audit | Audit log viewer (admin) – baseline UI | Read-only admin page listing audit events with filters (user, project, action, date) and paging; visible to admin role only. | FR-30, NFR-07 | Nivas | Should | 1 | 2 | 2026-10-29 | 2026-10-30 | Not started | Admin sees filtered audit events; non-admin receives 403; no edit controls exist. | S1-08, S1-11
S1-13 | Sprint 1 | Quality & testing | Negative authorization tests in CI | Automated API tests proving cross-project and unauthenticated access is refused; run on every PR. | NFR-02, FR-03 | Nivas | Must | 1 | 2 | 2026-10-30 | 2026-10-30 | Not started | Negative test suite runs in CI and fails the build on any authorization regression. | S1-10
S1-14 | Sprint 1 | Ingestion & provenance | Spike: extraction & embedding options | Compare Apache Tika + Tesseract vs Azure Document Intelligence on 5 sample documents; shortlist Sentence Transformers embedding model; note licences. | FR-05, NFR-15, NFR-21 | Krishna | Should | 1 | 2 | 2026-10-30 | 2026-10-30 | Not started | Spike note with extraction quality, OCR fallback behaviour, licence status and recommendation for Sprint 2. | S1-06
S1-15 | Sprint 1 | Sprint ceremonies | Sprint 1 review/demo + retrospective | Demo login → UI shell → authorized API call → audit entry; retro and backlog refinement for Sprint 2. | — | Both | Must | 0 | 2 | 2026-10-30 | 2026-10-30 | Not started | Demo delivered to stakeholders; retro actions recorded; Sprint 2 backlog refined. | All S1 tasks
S2-01 | Sprint 2 | Sprint ceremonies | Sprint 2 planning & source-approval checkpoint | Agree Sprint 2 goal; confirm approved document set and model licence status before ingestion starts. | FR-04, PRD §15 Phase 1 | Both | Must | 0 | 2 | 2026-11-02 | 2026-11-02 | Not started | Sprint goal agreed; approved sample sources listed with authorization basis; fallback agreed if approval pending. | S1-15
S2-02 | Sprint 2 | Sprint ceremonies | Daily stand-ups (5 × 15 min) | 15-minute daily stand-up at 09:30: progress, plan, blockers; update Status column. | — | Both | Must | 0 | 1.25 | 2026-11-02 | 2026-11-06 | Not started | Stand-up held each day; blockers logged on the board within the day. | None
S2-03 | Sprint 2 | Ingestion & provenance | Document ingestion pipeline | Read-only upload/import API; Apache Tika text & table extraction with Tesseract OCR fallback (or Document Intelligence if Azure chosen); stores versioned originals with source, authorization basis, version and extraction uncertainty. | FR-04, FR-05, FR-06 | Krishna | Must | 5 | 5 | 2026-11-02 | 2026-11-03 | Not started | PDF/DOCX/scanned samples ingested; each item records source, authorization basis and version; original retrievable by version; no writes to source systems. | S1-07, S1-14, S2-01
S2-04 | Sprint 2 | DevOps & CI/CD | CI/CD: container images & integration stage | Build/push API and UI images; integration-test stage with PostgreSQL + pgvector and Tika service containers; tag images per commit. | NFR-19, NFR-22 | Nivas | Must | 2 | 3 | 2026-11-02 | 2026-11-02 | Not started | Images built and tagged per commit; integration tests run against real Postgres/pgvector in CI. | S1-04, S1-06
S2-05 | Sprint 2 | Scientist UI | Document library UI | Upload documents into a project, show ingestion status, extracted text preview, extraction-uncertainty flag and version history. | FR-05, FR-06, FR-01 | Nivas | Must | 3 | 4 | 2026-11-03 | 2026-11-04 | Not started | Scientist uploads a file and sees status → extracted; versions listed; users see only their projects' documents. | S2-03
S2-06 | Sprint 2 | Retrieval & RAG | Chunking + embeddings into pgvector | Section-aware chunking with passage offsets; Sentence Transformers embeddings stored in pgvector with project, document-version and eligibility metadata; ineligible content skipped. | FR-08, NFR-06, NFR-10 | Krishna | Must | 3 | 4 | 2026-11-03 | 2026-11-04 | Not started | Only eligible passages with access metadata are indexed; each chunk links to document version and offsets; re-ingest is idempotent. | S2-03
S2-07 | Sprint 2 | Retrieval & RAG | Hybrid retrieval with server-side filters | PostgreSQL full-text + pgvector similarity with score fusion and reranking; project/document authorization filters applied in SQL before any content reaches the model. | FR-10, NFR-06, FR-15 | Krishna | Must | 3 | 4 | 2026-11-04 | 2026-11-05 | Not started | Top-k results relevant on 10-question evaluation set; tests confirm no unauthorized passage returned or passed to the model. | S2-06, S1-10
S2-08 | Sprint 2 | Scientist UI | Scientist Q&A UI: question → cited answer | Ask a question in project context; display answer with inline citations, citation panel linking to source passage and version, and a gaps & conflicts section. | FR-01, FR-11, FR-12, NFR-13 | Nivas | Must | 5 | 5 | 2026-11-04 | 2026-11-05 | Not started | Every claim shows a clickable citation opening the passage and version; unsupported claims visibly flagged; gaps section rendered. | S2-07, S2-09 (API contract)
S2-09 | Sprint 2 | Evidence Q&A workflow | LangGraph evidence Q&A workflow with human-review gate | LangGraph graph: retrieve → draft cited answer → validate citations/schema → interrupt for scientist review; Postgres checkpointer, allowlisted tools, explicit failure states; LLM via vLLM/Azure OpenAI adapter [model licence pending]. | FR-11, FR-12, FR-28, NFR-12, NFR-13 | Krishna | Must | 5 | 5 | 2026-11-05 | 2026-11-06 | Not started | Answers cite retrievable passages; uncited claims flagged; workflow resumes from checkpoint after restart; approval enforced by API; run id stored for provenance. | S2-07, model access (D-02)
S2-10 | Sprint 2 | Evidence Q&A workflow | Human-review gate UI | Reviewer actions on an answer: approve, reject or request more evidence with rationale; status and history shown. | NFR-12, FR-27, FR-30 | Nivas | Must | 2 | 3 | 2026-11-05 | 2026-11-05 | Not started | Review decision with rationale stored and audited; answer cannot be marked reviewed without API approval event. | S2-09
S2-11 | Sprint 2 | Data & audit | Audit view extensions for ingestion & review | Extend audit viewer with ingestion, retrieval and review events; filter by project and workflow run; export CSV. | FR-30, NFR-07, NFR-10 | Nivas | Should | 1 | 2 | 2026-11-06 | 2026-11-06 | Not started | Auditor reconstructs who asked, which sources were cited and who approved for a demo answer. | S1-12, S2-09
S2-12 | Sprint 2 | Quality & testing | Retrieval security & provenance tests | Automated tests: cross-project leakage, ineligible content excluded, every citation resolves to passage + version + workflow run. | FR-10, NFR-06, NFR-10 | Krishna | Must | 1 | 2 | 2026-11-06 | 2026-11-06 | Not started | Suite green in CI; zero unauthorized passages across test projects; 100% of demo citations resolvable. | S2-07, S2-09
S2-13 | Sprint 2 | Quality & testing | End-to-end UI tests | Playwright flow: login → upload → ask → cited answer → review decision; runs in CI against the compose stack. | NFR-02, NFR-12 | Nivas | Should | 1 | 2 | 2026-11-06 | 2026-11-06 | Not started | E2E suite passes in CI; screenshots attached to the sprint demo. | S2-08, S2-10
S2-14 | Sprint 2 | Sprint ceremonies | Sprint 2 review/demo + retrospective | Demo to scientists: ingest approved document → ask question → cited answer with provenance → review gate → audit trail; retro; refine Phase 1 backlog (verification queue FR-07 next). | PRD §15 Phase 1 | Both | Must | 0 | 2 | 2026-11-06 | 2026-11-06 | Not started | Scientist feedback captured; retro actions recorded; next sprint backlog prioritised. | All S2 tasks

## Daily Schedule
Daily Schedule – 10 working days (26 Oct – 6 Nov 2026)
Dates flow from the Sprint 1 start date on Overview (working days only). Task IDs refer to the Sprint Backlog.
Date | Day | Sprint | Krishna – backend / AI / data | Nivas – frontend / platform / DevOps | Ceremony / milestone
2026-10-26 | Monday | Sprint 1 | S1-01 Sprint planning; S1-03 Phase 0 alignment (sources, IdP, model licence); S1-05 FastAPI skeleton – layout, config, health endpoints | S1-01 Sprint planning; S1-03 Phase 0 alignment; S1-04 repository, branching & CI pipeline (lint, tests, secret scan) | Sprint 1 planning 10:00 (2 h); stand-up 09:30
2026-10-27 | Tuesday | Sprint 1 | S1-03 Phase 0 decision log; S1-05 OpenAPI, structured logging, OTel hooks; S1-07 start PostgreSQL/pgvector schema | S1-04 CI pipeline complete; S1-06 Podman dev environment (API, Postgres/pgvector, Keycloak, Nginx, Tika) | Stand-up; identity provider decision needed – Keycloak vs Entra ID [confirm with client]
2026-10-28 | Wednesday | Sprint 1 | S1-07 schema v1 + Alembic migrations; S1-10 start JWT validation & project/role authorization | S1-06 dev environment complete; S1-08 React/Vite UI shell; S1-09 start OIDC SSO integration | Stand-up; milestone: one-command dev environment ready
2026-10-29 | Thursday | Sprint 1 | S1-10 authorization middleware + object-level checks; S1-11 audit log baseline (append-only) | S1-08 three workspace views; S1-09 SSO login, token refresh, gateway check; S1-12 start audit viewer | Stand-up; milestone: login → authorized API call end to end
2026-10-30 | Friday | Sprint 1 | S1-11 audit baseline complete; S1-14 extraction & embedding spike; S1-15 demo & retro | S1-12 audit viewer; S1-13 negative authorization tests in CI; S1-15 demo & retro | Sprint 1 review/demo 14:00 + retrospective 15:00; client source approval due
2026-11-02 | Monday | Sprint 2 | S2-01 Sprint planning; S2-03 ingestion pipeline – upload/import API, Tika extraction, versioned originals | S2-01 Sprint planning; S2-04 CI/CD container images + integration-test stage (pgvector, Tika) | Sprint 2 planning 10:00 (2 h); model licence decision needed
2026-11-03 | Tuesday | Sprint 2 | S2-03 Tesseract OCR fallback, provenance & extraction uncertainty; S2-06 start chunking | S2-05 document library UI (upload, status, versions) | Stand-up
2026-11-04 | Wednesday | Sprint 2 | S2-06 chunking + embeddings into pgvector with access metadata; S2-07 start hybrid retrieval | S2-05 library UI complete; S2-08 start scientist Q&A UI | Stand-up; milestone: ingest → index flow working
2026-11-05 | Thursday | Sprint 2 | S2-07 hybrid retrieval, reranking & server-side filters; S2-09 LangGraph evidence Q&A workflow | S2-08 Q&A UI with citation panel & gaps section; S2-10 human-review gate UI | Stand-up; milestone: question → cited answer end to end
2026-11-06 | Friday | Sprint 2 | S2-09 checkpoints, review interrupt & audit events; S2-12 retrieval security & provenance tests; S2-14 demo & retro | S2-11 audit view extensions; S2-13 end-to-end UI tests; S2-14 demo & retro | Sprint 2 review/demo with scientists 14:00 + retrospective 15:00
Formulas:
Date = WORKDAY([Date, row above],1)

## Gantt
Gantt – Sprint 1 & Sprint 2 task timeline by owner
Legend | Bars are driven by Start/End dates in the Sprint Backlog → | Krishna | Nivas | Both | Sprint 1 (26–30 Oct) |  |  |  |  | Sprint 2 (2–6 Nov)
ID | Task | Owner | Start | End | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06
S1-01 | Sprint 1 planning & PRD walkthrough | Both | 2026-10-26 | 2026-10-26 | Both
S1-02 | Daily stand-ups (5 × 15 min) | Both | 2026-10-26 | 2026-10-30 | Both | Both | Both | Both | Both
S1-03 | Phase 0 alignment: scope, sources, access & success criteria | Both | 2026-10-26 | 2026-10-27 | Both | Both
S1-04 | Repository, branching & CI pipeline | Nivas | 2026-10-26 | 2026-10-27 | Nivas | Nivas
S1-05 | FastAPI backend skeleton | Krishna | 2026-10-26 | 2026-10-27 | Krishna | Krishna
S1-06 | Podman dev environment | Nivas | 2026-10-27 | 2026-10-28 |  | Nivas | Nivas
S1-07 | PostgreSQL/pgvector schema v1 + migrations | Krishna | 2026-10-27 | 2026-10-28 |  | Krishna | Krishna
S1-08 | React/Vite UI shell | Nivas | 2026-10-28 | 2026-10-29 |  |  | Nivas | Nivas
S1-09 | SSO integration (OIDC) – Keycloak or Entra ID [confirm with client] | Nivas | 2026-10-28 | 2026-10-29 |  |  | Nivas | Nivas
S1-10 | Project & role-based authorization in API | Krishna | 2026-10-28 | 2026-10-29 |  |  | Krishna | Krishna
S1-11 | Audit log baseline | Krishna | 2026-10-29 | 2026-10-30 |  |  |  | Krishna | Krishna
S1-12 | Audit log viewer (admin) – baseline UI | Nivas | 2026-10-29 | 2026-10-30 |  |  |  | Nivas | Nivas
S1-13 | Negative authorization tests in CI | Nivas | 2026-10-30 | 2026-10-30 |  |  |  |  | Nivas
S1-14 | Spike: extraction & embedding options | Krishna | 2026-10-30 | 2026-10-30 |  |  |  |  | Krishna
S1-15 | Sprint 1 review/demo + retrospective | Both | 2026-10-30 | 2026-10-30 |  |  |  |  | Both
S2-01 | Sprint 2 planning & source-approval checkpoint | Both | 2026-11-02 | 2026-11-02 | [5 empty] | Both
S2-02 | Daily stand-ups (5 × 15 min) | Both | 2026-11-02 | 2026-11-06 | [5 empty] | Both | Both | Both | Both | Both
S2-03 | Document ingestion pipeline | Krishna | 2026-11-02 | 2026-11-03 | [5 empty] | Krishna | Krishna
S2-04 | CI/CD: container images & integration stage | Nivas | 2026-11-02 | 2026-11-02 | [5 empty] | Nivas
S2-05 | Document library UI | Nivas | 2026-11-03 | 2026-11-04 | [6 empty] | Nivas | Nivas
S2-06 | Chunking + embeddings into pgvector | Krishna | 2026-11-03 | 2026-11-04 | [6 empty] | Krishna | Krishna
S2-07 | Hybrid retrieval with server-side filters | Krishna | 2026-11-04 | 2026-11-05 | [7 empty] | Krishna | Krishna
S2-08 | Scientist Q&A UI: question → cited answer | Nivas | 2026-11-04 | 2026-11-05 | [7 empty] | Nivas | Nivas
S2-09 | LangGraph evidence Q&A workflow with human-review gate | Krishna | 2026-11-05 | 2026-11-06 | [8 empty] | Krishna | Krishna
S2-10 | Human-review gate UI | Nivas | 2026-11-05 | 2026-11-05 | [8 empty] | Nivas
S2-11 | Audit view extensions for ingestion & review | Nivas | 2026-11-06 | 2026-11-06 | [9 empty] | Nivas
S2-12 | Retrieval security & provenance tests | Krishna | 2026-11-06 | 2026-11-06 | [9 empty] | Krishna
S2-13 | End-to-end UI tests | Nivas | 2026-11-06 | 2026-11-06 | [9 empty] | Nivas
S2-14 | Sprint 2 review/demo + retrospective | Both | 2026-11-06 | 2026-11-06 | [9 empty] | Both

## Capacity
Capacity & Utilisation – Krishna and Nivas, Sprints 1–2
Planned hours come live from the Sprint Backlog (SUMIFS). "Both" tasks count in full for each developer. Utilisation above the threshold turns red.
Capacity inputs | Value | Unit / note
Focus hours per day | 6 | h/day per developer
Working days per sprint | 5 | days (Mon–Fri)
Target load | 80% | of available hours (~80%)
Over-allocation threshold | 90% | red above this
Developer | Sprint | Available (h) | Target (h) | Own tasks (h) | Shared "Both" (h) | Planned (h) | Utilisation % | Buffer (h) | Tasks (#) | Load status
Krishna | Sprint 1 | 30 | 24 | 18 | 7.25 | 25.25 | 84.17% | 4.75 | 9 | On target
Nivas | Sprint 1 | 30 | 24 | 18 | 7.25 | 25.25 | 84.17% | 4.75 | 10 | On target
Krishna | Sprint 2 | 30 | 24 | 20 | 5.25 | 25.25 | 84.17% | 4.75 | 8 | On target
Nivas | Sprint 2 | 30 | 24 | 19 | 5.25 | 24.25 | 80.83% | 5.75 | 9 | On target
Total (both developers) | Sprints 1–2 | 120 | 96 | 75 | 25 | 100 | 83.33% | 20 | 36 | On target
Check: person-hours in backlog minus planned (should be 0) | [5 empty] | 0
Note: daily stand-ups (1.25 h), planning (2 h) and review/retro (2 h) are included as "Both" tasks, so ~5 h of each sprint goes to ceremonies.